## Deliverables Table
Items | Estimated Time (hrs) | Actual Time (hrs) | Completed? | % of Scoped Work Completed | % of Time Used | I took -- times longer than expected
Task Diagram | 1 | 2 | Y
Create Risk Register | 0.5 | 0.25 | Y
Create Deliverables Table | 0.5 | 0.5 | Y
Summarize Work | 0.5 | 0.5 | Y | 5.618 | 7.3034 | 1.3
Declare Global Variables and Data Structures | 1 | 0.5 | Y
Revise Task Diagram | 0.5 | 0.5 | Y
Begin Implementing Structure in Simplicity | 1 | 7.5 | Y
Summarize Work | 0.5 | 2 | Y | 6.7416 | 23.5955 | 3.5
Revise Globals & Task Diagram | 0.5 | 1 | Y
Finish Implementing Structure | 8 | 0 | Y
Begin Implementing Details Task by Task | 8 | 11 | Y
Summarize Work | 0.5 | 1 | Y | 38.2022 | 29.2135 | 1.1889
Implement Details Task by Task | 8 | 6.5 | Y
Revise Globals & Task Diagram | 0.5 | 1 | Y
Summarize Work | 0.5 | 0.5 | Y | 20.2247 | 17.9775 | 0.88889
Revise Globals & Task Diagram | 0.5 | 0.5 | Y
Debugging | 12 | 16 | Y
Summarize Work | 0.5 | 0.5 | Y | 2.2472 | 2.2472 | 1
Total | 44.5 | 51.75
1.1629

## Risk Register
Risk Register | Probability | Impact | Risk | Recognized | ROAM & Date | How
Significant Simplicity Errors | 40 | 60 | 2400 | 2023-03-17 | A | Out of my control
Sickness flares up | 20 | 40 | 800 | 2023-03-17 | A | Out of my control and unlikely
Super Busy in coming weeks | 60 | 80 | 4800 | 2023-04-07 | M | Completed a lot of my code and responsibilities outside of this class
Loses mini-USB | 20 | 20 | 400 | 2023-04-13 | M | Roommate has backup charger
Broken board | 10 | 90 | 900 | 2023-04-20 | A | Out of my control and unlikely
Can't get code working | 20 | 100 | 2000 | 2023-04-26 | A | Out of my control and unlikely