## Deliverables Table
Items | Estimated Time (hrs) | Actual Time (hrs) | Completed? | % of Scoped Work Completed | % of Time Used | I took -- times longer than expected
Task Diagram | 1 | 2 | Y
Create Risk Register | 0.5 | 0.25 | Y
Create Deliverables Table | 0.5 | 0.5 | Y
Summarize Work | 0.5 | 0.5 | Y | 7.4627 | 9.7015 | 1.3
Declare Global Variables and Data Structures | 1 |  | N
Revise Task Diagram | 0.5 |  | N
Begin Implementing Structure in Simplicity | 1 |  | N
Summarize Work | 0.5 |  | N
Revise Globals & Task Diagram |  |  | N
Finish Implementing Structure | 1 |  | N
Begin Implementing Details Task by Task | 4 |  | N
Revise Globals & Task Diagram | 0.5 |  | N
Summarize Work | 0.5 |  | N
Implement Details Task by Task | 4 |  | N
Revise Globals & Task Diagram | 0.5 |  | N
Summarize Work | 0.5 |  | N
Implement Details Task by Task | 4 |  | N
Revise Globals & Task Diagram | 0.5 |  | N
Debugging | 12 |  | N
Summarize Work | 0.5 |  | N
Total | 33.5 | 3.25

## Risk Register
Risk Register | Probability | Impact | Risk | Recognized | ROAM & Date | How
Significant Simplicity Errors | 40 | 60 | 2400 | 2023-03-17 | O | Wes to come up with mitigation strategy
Sickness flares up | 20 | 40 | 800 | 2023-03-17 | A | Out of my control and unlikely