## Deliverables Table
Items | Estimated Time (hrs) | Actual Time (hrs) | Completed? | % of Scoped Work Completed | % of Time Used | I took -- times longer than expected
Task Diagram | 1 | 2 | Y
Create Risk Register | 0.5 | 0.25 | Y
Create Deliverables Table | 0.5 | 0.5 | Y
Summarize Work | 0.5 | 0.5 | Y | 5.618 | 7.3034 | 1.3
Declare Global Variables and Data Structures | 1 | 0.5 | Y
Revise Task Diagram | 0.5 | 0.5 | Y
Begin Implementing Structure in Simplicity | 1 | 7.5 | Y
Summarize Work | 0.5 | 2 | Y | 6.7416 | 23.5955 | 3.5
Revise Globals & Task Diagram | 0.5 | 1 | Y
Finish Implementing Structure | 8 | 0 | Y
Begin Implementing Details Task by Task | 8 | 11 | Y
Summarize Work | 0.5 | 1 | Y | 38.2022 | 29.2135 | 1.1889
Implement Details Task by Task | 4 |  | N
Revise Globals & Task Diagram | 0.5 |  | N
Summarize Work | 0.5 |  | N
Implement Details Task by Task | 4 |  | N
Revise Globals & Task Diagram | 0.5 |  | N
Debugging | 12 |  | N
Summarize Work | 0.5 |  | N
Total | 44.5 | 26.75

## Risk Register
Risk Register | Probability | Impact | Risk | Recognized | ROAM & Date | How
Significant Simplicity Errors | 40 | 60 | 2400 | 2023-03-17 | A | Out of my control
Sickness flares up | 20 | 40 | 800 | 2023-03-17 | A | Out of my control and unlikely
Super Busy in coming weeks | 60 | 80 | 4800 | 2023-04-07 | O | Moved back to owned as previous strategy is not feasible, attack plan TBD
Loses mini-USB | 20 | 20 | 400 | 2023-04-13 | M | Roommate has backup charger